## Latest Defects
Defect ID | Jira ID | PRIORITY | DESCRIPTION | Connect QA Remarks | Assigned to Team | Defects status | ETA | Comment
1 | MCKB2B-50723 | High | Data inconsistencies between Connect Portal and MCAP Portal (FQA) | Message from BASIS - DNS switching done and portal redirected to fqapp01 instead of fqa. | BASIS | Closed
2 |  | High | SAP Team - unable to send Ack and Invoice Ack due to RFC's in SAP are not active | Resolution obtained from BASIS. It works now | BASIS | Closed
3 |  | High | MCAP POD Microservice error | we are facing issue while accessing Pod microservice from SAP NetWeaver and we are getting “Handshake Failures”. | BASIS | Closed
4 |  | High | Invoice generation not working for MCAP | Invoice pdf and download of files are not working - Files are not generating/getting downloaded in FQA environment. | BASIS | Closed
5 | MCKB2B-51137 | High | Ofiles not getting generated | O File - file not generated at location "/data/export/integrations/edi861/pending/ after running edi861ExportJob | L3 OPS | Closed | Vaishali to retest on 23rd Aug | Unab
6 |  | Low | Logs are not displayed for integrations INT-033 MPB qty check, INT-013 Quick order and INT-049 | Logs not genretaing in following path mcod-007.oc.mckesson.com:9002/uat/cluster/logs/uat1/frontoffice_1/hybris.log | L3 OPS | Closed
7 | MCKB2B-50782 | High | Order status is not updating to "Invoice" in UAT1 |  | L3 OPS | Closed
8 | MCKB2B-50867 | High | AWP Price [Higher Price] not updated at Connect Side, even when the item AWP price configured in SAP | SAP has triggered the job, that drops mckiupld_item.dat file to Connect. (File Path /data/import/integrations/mastercatalog/pending). Gopikrishna from SAP is working on it (Defect ID #174 is raised by him). We will then trigger productDataLoaderJob cronJob, that will update products info into database from that file. (The cronjob will be triggered, after L3 takes a backup). AWP pricing getting updated in Connect will be verified post that | MDM | Closed
9 |  | High | For account 021540, Screens are not getting opened due to insertion of wrong records whose length is not acceptable in MCAP. | the issue was corrected by BASIS. Its retested and found to be working fine | BASIS | Closed
10 | MCKB2B-51018 | High | INT -077 : DcQuantity Check Webservice response have one required field missing "DistributionCenterId""" | It was working as expected until last week | SAP | Closed |  | Accounts 800000 and 800001 were having issues. Received data for other accounts
11 | MCKB2B-50778 | High | INT-111 : Order status check API failing with Server error 500 | Encountering an error while executing a request to the following endpoint: http://ws-qa-internal.mckesson.com:9898/1.0.1/ecc-orderlookp/crm/orderstatus. The Connect service is making a request to this address to the EAI system, which in turn queries SAP. The error seems to arise on the EAI side. @Suresh, Saikiran - can you pls check on this ? | EAI | Closed
12 |  | High | O Files - Order Status is not updating to Acknowledgement | New orders were created today and those are reflecting in SAP (Jyoti from SAP verified and confirmed). PO# edi_861_23, PO# edi_23_24_02. Both are not in acknowledged status | L3 OPS | Closed
13 |  | Medium | SFR order with below details raised by SAP team with 2 different items attached to order. Order is visible at connect side, with only 1 item. SFR IDOC ->7578231020; Account-027553; PO- 1.1AZURE_33 | Items added from SAP to above order -> 3785805(dropship) and 2144566(pharma). Item visible at connect for above order->3785805(dropship) only. L3 is still analyzing the issue. We will have the updates tomorrow | L3 OPS | Closed
14 | MCKB2B-50729 | High | INT-073 ¦¦ Itemadd-delete.dat Files are generated from SAP, but not reached to Connect | After SAP runs the job, the add_del001.dat file is moved from /shared/SMOexport/add_del001.dat to the Connect file path "shared/export-PRD" instead of "/shared/export-UAT". This was explained to Mamatha for further investigation. It is expected to be a problem at BASIS side. Mamatha said, she will get back post the discussion with BASIS | BASIS | Closed
15 | MCKB2B-50871 | Medium | MOQ File - Passed from EAI but not reached Connect. | We retested and could find the file reaching successfully | EAI | Closed
16 | MCKB2B-50870 | Medium | PO and Inv Acks: Passed from EAI but not reached Connect | Retested. Not a defect anymore | EAI | Closed
17 | MCKB2B-50401 | Medium | Jobs for processing FORMCUST and FORMSLOT files are failing | Retested. Both the files reaching Connect, is verified successfully | EAI | Closed
18 |  | High | iDOC not reaching Connect. SFR IDOC: 7578230928; Account: 27553; PO: AZURE_3 | It was retested. iDOC was verified to have reached connect, | L3 OPS | Closed
19 | MCKB2B-50775 | High | On selecting the DC link, DC Stock page is empty even when the qty is available on the search page for the item selected | BASIS @Kalli, Venkatreddy (2) - As per analysis from SAP, the connection goes to TST system, instead of RQB. However, there is also an update from SaiKiran Mallamm, that the issue is resolved and he is able to get successful response. Pls retest. | BASIS | Closed
20 | MCKB2B-50985 | High | On catalogue search page DC quantity/Available quantity is appearing as zero. | SAP team added DC quantity for some of the items related to following accounts in Connect: 21540, 745391, 800000, 800001. However, even though the SAP team has added the DC quantity, it still shows DC quantity as zero | SAP | Closed
21 | MCKB2B-50642 | High | INT-063 ¦¦ On Catalogue search following fields 'Est. Net Price', 'Purchase Price', and 'Unit Price' are displaying with a question mark (?) instead of presenting the correct figures | This issue is again happening in UAT1 and UAT2 and also it's happening intermittently for some accounts Maksim Ivantsou Added: SAP doesn't send prices, please contact to SAP. | SAP | Closed
22 | MCKB2B-51216 | High | MCAP shows Partial for fully received order. | Shows Partial in API response, though it is "Finalized" in UI | L3 OPS | Closed |  | Unable to reproduce this. Also checked code and we haven’t found a way to make consignment entries not finalized during finalization from connect ui. We only have suggestion that either orders that were finalized were somehow corrupted, or at the moment of finalization of those orders we had some code with featureTesting on UAT1 which broke this functionality. We suggest that you should create new orders and finalize them, since I don’t see any issues with them.
23 | MCKB2B-50863 | High | CSOS Signing – Issue at Connect Side - Express 222 error | Below is the response from Legisym team. Thank you, Dmytro. It looks like the issue is in the step which your system pulls a login token from our application. I checked our logs and found that we are returning this error message back to you: { "signature":"41328eaffa8ffee419165f7ace33ad7bb4f95f0dad77114ff3f4bcdbff8e6d08", "payload":{ "responseType":"generateLoginToken", "responseData":{ "success":"FALSE", "errors":{ "LTWS002":"PROVIDED USERNAME IS NOT FOUND" } } } } I looked at the login token request and think I found the problem. In your request, the user id is "uatadm8", but the user id that exists in Express222 for this test user is "uatadm8_batch". Because of the mismatch in user ids, it is returning the above error message. I am also including one of the login token requests that we received below to show the incorrect user id. To correct this, it will need to be updated to "uatadm8_batch" and then it should work without any issues. { "signature":"c6aeaa5d964d515e068cb1552fa3bc82a1db4b4d4d29179ccdccee123c9dfd1e", "payload":{ "requestType":"generateLoginToken", "requestDateTime":"Wed, 07 Aug 2024 12:50:03 GMT", "requestData":{ "serviceContractToken":"9F4ABEBA-FB12-4CF2-8324-FBB898C5DC6B", "partnerDeaNumber":"AS2778377", "userName":"uatadm8" } } } Sincerely, Andrew Legisym Support | Legisym | closed
24 | MCKB2B-51255 | High | http://ws-qa-internal.mckesson.com:8055/PF005_SMOELA_Pricing3_BIMWeb/sca/InvokeInterfaceExport1 link not returning prices | IIB is down & mulesoft is working instead. PROD has IIB though. IIB was tested to work fine until Aug 9th. Later today, it is confirmed to be fixed. Need to retest | MDM | Closed
25 | MCKB2B-51273 | High | INT-109 : order update API getting server error in response |  | SAP | Open |  | Ticket will be taken into investiation today by Dymtro
26 | MCKB2B-51171 | Medium | INT-016 Order created for client ID ENTRX not visible on UI | As per Maksim Ivantsou -> enterprise RX orders (ENTRX) do not appear in the UI and this is an expected result he order is created correctly and can be found in the database. | L3 OPS | Closed
27 | MCKB2B-51254 | Low | On selecting FTP price/product export, Internal server Error is displayed | Assigned to Libra | L3 OPS | Closed
28 | MCKB2B-50834 | Medium | EDI 861 files are not generated at location "/data/uat/export/integrations/edi861/pending/processed" | Expected result : file must be generated in “/data/export/integrations/edi861/pending/processed/” folder after job (edi861ExportJob) is run Actual Result - /data/export/integrations/edi861/pending/processed/” in this path no file generated though processed folder got updated with same date and time the job ran | L3 OPS | Closed | Vaishali to retest on 23rd Aug | It was working and closed. However issue cropped up again and we reopend following ticket MCKB2B-51137 for this issue
29 | MCKB2B-50638 | Medium | UAT 1 Backoffice ¦¦ INT-107 ¦¦ Account Buyer Category field is not updating | BUYERCATEGORY field should be populated for a given account, in line with accounts_buyer.txt file | L3 OPS | Closed |  | Working fine . Defect closed
30 | MCKB2B-51246 | High | DSCSA Reports when submitted not moving to Completed status | Anna restarted the R&A Application , now its working | L3 OPS | Closed |  | Yet to take into Investigation.Uanble to Provide ETA
31 | MCKB2B-51172 | Medium | INT-111 : GET Order status check API response is always order not found even adding correct details of created order |  | L3 OPS | Closed |  | Yet to take into Investigation.
32 | MCKB2B-51252 | Medium | Facing HTTP STATUS 500 Error Javax.servlet.jspexception : Cannot find Bean under time slots |  | L3 OPS | Closed |  | This is deployment issue . Changing to Libra team from EAI
33 | MCKB2B-51368 | Medium | INT-068b MPB Item Exclusions : exclusion items from MPB file are not found in UI getting search error as "no product matches found" |  | L3 OPS | closed |  | Yet to take into Investigation.
34 |  | High | "500 Connection Timeout Error in MCAP Portal When Accessing 'For Approval' or 'Open' Menu Under 'Transactions' Section" Steps to reproduce: S1>Open your web browser and navigate tothe following URL: https://fqaapp01.mckesson.com:53001/mcap/public/frameset_top_html.jsp S2>Enter your valid username and password to log in to the MCAP portal.(RQABD11, MCAP@123, 021540) S3>Once logged in,will be directed to the customer search page. Here, enter valid account details in the 'McKesson Account Numbers' textbox. S4>Click the 'Submit' button, system will then take you to the 'National Reporting Numbers' page. S5>On the 'National Reporting Numbers' page, enetr the provided account and click 'Continue'. S5>Now, under the 'Transactions' section, click on either the 'For Approval' or 'Open' menu. Actual Result: Observe the behavior of the page. It may load for a while before displaying a '500 connection time out' message. |  | SAP | Closed
35 |  | High | File MFGR_DISC_TOOL_TIP.txt not reaching Connect, after the MFT job is run for "MFR_Discounts" integration | File transfers from EAI , then owner should be mftuser.but, in below mentioned screenshot highlighted file was transferred different user group. note ->below is file generated from earlier job trigger by SAP | SAP | Closed
36 | MCKB2B-51425 | Medium | INT -073 Account Item Add Delete : itemadd_delete_20240816.impex" file generating directly at "archive" folder instead of pending folder with additional error file |  | L3 OPS | Closed |  | Yet to take into Investigation.
37 |  | High | INT-101 NPI Lookup Webservice-On selecting NPI Lookup table getting "Service is temporary unavailable. Please try again later."error messgae Calling End point: http://ws-qa-internal.mckesson.com:8071/MckWebServices/connect/bw/getnpidata. Steps to reproduce: 1.Login in connect UAT1(https://testwcm.mckesson.com/content) 2.Select account 800001 and item 3482288 3.Add item to the cart and submit the order 4.NPI lookup page is displayed , now select continue and click on search button 5.Service is temporary unavailable. Please try again later. error message is displayed Logs: Request:?npiNo=12 Response:Unsupported Method: GET. |  | EAI | Closed | On Selecting NPI Lookup table, getting the error unable to fetch National Provider Identity information
38 | MCKB2B-51476 | Medium | "Unable to retrieve Orders Based on Status (Submitted, Invoiced, Finalized) on Order List Page" |  | L3 OPS | Closed |  | Working fine now
39 |  | High | MCAP page loads as plain text. The images & icons are not getting loaded. Also getting SSL error. Link : https://fqaapp01.mckesson.com:53001/mcap/public/frameset_top_html.jsp?ver |  | SAP | Closed
40 | MCKB2B-51477 | High | INT-067 MPB pricing -> empty core files received from SAP |  | SAP | Closed
41 |  | High | (MCAP) TPC link integration is not working since YVCRR_DOC_CENTRAL program is not executing successfully |  | EAI | Closed
42 | MCKB2B-51668 | High | Invoice Status updates for Orders not reaching to Connect Steps to reproduce the issue: S1>Log into the Connect system. S2>Create multiple orders and set status to 'Submitted' and then to invoiced s3>Send list of orders to the SAP team, and ask to change the status of these orders first to Acknowleged and then to 'Invoice'. S4>Log back into the Connect system. and verify if the status of these orders has been updated to 'Invoice'. Actual Result: The status of the orders in the Connect system is not changing to 'Invoice' even after the SAP team has made the changes. Expected Result: The status of the orders in the Connect system should change to 'Invoice' after the SAP team has made the changes. | Kindly Note: Seems SAP/EAI issue . There are no new invoices available in the STG0.T_ACK_WRK2 table. The invoices that SAP shared are duplicates and can be found in the table, but they are not the most recent ones. | EAI | Closed
43 | MCKB2B-51760 | High | Orders are missing in NGO for account 800001 dated before 21 Aug 2024. |  | L3 OPS | Closed
44 | MCKB2B-51782 | Medium | Portal Account management DB is not in SYNC with Portal Mirror DB in ITE(UAT1) environment after running the b2b-connect-portal-account-sync-template-ite cron job from GCP |  | Portal | Closed
45 | MCKB2B-51805 | High | INT-038-Discrepancies in Account details which was reinserted in Backoffice after running the cronjob. |  | L3 OPS | Closed
46 | Associated with Defect #25 | High | INT-109 : Creating wegman csos order in awaiting signature is reaching as esigned at SAP User -uatadm8 orderId: 260285013 poNumber: Wegman_02 Account- 112723(Wegman Account) |  | SAP | Open
47 |  | High | Http error issue with Content repository I1 while testing third party credits for MCAP Portal. |  | SAP | Open |  | 09/12: For TPC, the program is failing to attach image. when debugged could see this is failing at below standard archiving object link FM, where it’s trying to attach the image to the YI document. We need further help why exactly this is failing here with http error.
48 |  | High | IIS Files DPO_DE_MATERIAL_CUR.dat and DPO_DE_VENDOR_CUR.dat were transferred to server mckcqa-018.oc.mckesson.com How ever Connect is expecting the files in target server ddcdxtam01.mckesson.com Source: sappoc-qa-007 Path: /data/PHR/xfer/outbound/smo/ Target : ddcdxtam01.mckesson.com |  | EAI | Open
49 |  | High | MCAP Portal Unable to Login Due to ALEREMOTE user is Locked |  | SAP | Open
50 |  | High | FHA Application is Not accessable due to two issues - Certficate missed in the Local instance directory ( Previously it read from central location ) Certificate needs to Be signed |  | SAP | Open
51 | MCKB2B-52215 | High | Credit Memo import files have no data even after return order acknowledged and invoiced. Steps to follow -> Step 1_) login to NGO application and click on return → create return Step 2) Add item to return with select invoice date and return reason Step 3) Submit the return → status will be submitted Step 4) Request SAP team to Acknowledge the return → After acknowledge status of return order changes to acknowledge Step 5) Request SAP team to invoice the return order → SAP invoice the return order from their end Step 6) Pento scripts runs and credit Memo import file gets generated at folder → /data/import/integrations/creditmemo/pending Step 7) Run cron job CreditmemoImportJob and then UpdateReturnStatusJob Step 8 - File will be at below location ->/data/uat/import/integrations/creditmemo/archive Expected Result - > File generated must have return order details and Return order status must change to invoice at connect end Actual result → Credit memo files generated have no data and Return order remains in acknowledged status | INT-059 ,036,036b | EAI | Open